

Project Status Summary

Risk Mitigation Metric for Multifactor Authentication Systems (DARPA RA-11-52)

Report Date: 13-Oct-2013  
Project Manager: Bob O’Brien  
Technical Lead: Stephen Paul King

# Project Schedule

Overall Project is **Behind Schedule**.

* Sprint 6 still in progress
* Test Session Acquisition in progress

# Project Budget

Project is on budget:

* Invoice for lease of AWS Virtual Machine environment will be forwarded as soon as we get one from the vendor.

# Risks and Issues

Risks and Issues were last reviewed by the Project Team on 13-Oct-2013.

Initial connection problems that some testers had with the virtual camera and microphone software were resolved, but it is proving impossible due to latency and resolution issues to rely on this software with multiple testers. While we expect that, with time, these issues can be resolved, for sake of expediency we have decided to deploy the test system in an alternate fashion – making the executable available via “google drive” for testers to use locally on their desktops.

A new issue arose when our testing uncovered some algorithmic errors in the AT&T Voice system we are using as a Voice Authenticator. We are working with AT&T developers to see these problems resolved, but delays have required us to extend testing by another week.

# Overall Project Health

Project is behind schedule. Late issues encountered over the past two weeks during data collection have required us to extend the test collection phase of the effort, with final analysis and reporting being moved as well. We now anticipate completing things and making final delivery on Monday, October 28th, 2013.

# Report Prepared By…

Robert O’Brien  
13-October-2013