## Schedule
June
Activity | Activity Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Milestone 1 | Prepare White Paper on three methodologies | bar: 1 to 23
1.a | Research Bayesian and MaxEnt methodologies
1.b | Research MrE methodology (Clarkson)
1.c | Complete White Paper | bar: 1 to 23
1.d | Clarkson review of White Paper (Clarkson) | bar: 1 to 23
1.x | Project Management
Milestone 2 | Identify initial requirements for RMM and "bench tester" | bar: 1 to 23
2.a | Identify basic interface requirements of components
2.b | Identify basic interface requirements of components (Sub)
2.c | Identify basic interface requirements of components (Univ)
2.d | Specify high-level requirements for "problem model"
2.e | Specify high-level requirements for "problem model" (Sub)
2.f | Specify high-level requirements for "problem model" (Univ)
2.g | Specify first-pass minimum API requirements | bar: 1 to 23
2.h | Specify first-pass minimum API requirements (Sub) | bar: 1 to 23
2.x | Project Management
July
Activity | Activity Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Milestone 1 | Prepare White Paper on three methodologies | bar: 18
1.a | Research Bayesian and MaxEnt methodologies | bar: 1 to 3; 5; 8 to 12; 15
1.b | Research MrE methodology (Clarkson) | bar: 1 to 3; 5; 8 to 12; 15
1.c | Complete White Paper | bar: 12; 15 to 18
1.d | Clarkson review of White Paper (Clarkson) | bar: 17 to 18
1.x | Project Management | bar: 1 to 3; 5; 8 to 12; 15 to 18
Milestone 2 | Identify initial requirements for RMM and "bench tester" | bar: 12
2.a | Identify basic interface requirements of components | bar: 1 to 3; 5; 8 to 10
2.b | Identify basic interface requirements of components (Sub) | bar: 1 to 3; 5; 8 to 10
2.c | Identify basic interface requirements of components (Univ) | bar: 1 to 3; 5; 8 to 10
2.d | Specify high-level requirements for "problem model" | bar: 1 to 3; 5; 8 to 10
2.e | Specify high-level requirements for "problem model" (Sub) | bar: 1 to 3; 5; 8 to 10
2.f | Specify high-level requirements for "problem model" (Univ) | bar: 1 to 3; 5; 8 to 10
2.g | Specify first-pass minimum API requirements | bar: 8 to 12
2.h | Specify first-pass minimum API requirements (Sub) | bar: 8 to 12
2.x | Project Management | bar: 1 to 3; 5; 8 to 12
MIlestone 3 | Development Sprint 1 | bar: 26
3.a | Identify targets for Sprint 1 | bar: 15
3.b | Identify targets for Sprint 1 (Sub) | bar: 15
3.c | Perform sprint 1 analysis, coding & testing | bar: 15 to 19; 22 to 26
3.d | Perform sprint 1 analysis, coding & testing (Sub) | bar: 15 to 19; 22 to 26
3.e | Perform sprint 1 analysis, coding & testing (Univ) | bar: 15 to 19; 22 to 26
3.f | Review sprint 1 objectives and deliverables | bar: 26
3.g | Review sprint 1 objectives and deliverables (Sub) | bar: 26
3.x | Project Management | bar: 15 to 19; 22 to 26
MIlestone 4 | Development Sprint 2
4.a | Identify targets for Sprint 2 | bar: 29
4.b | Perform sprint 2 analysis, coding & testing (Clarkson) | bar: 29 to 31
4.c | Perform sprint 2 analysis, coding & testing | bar: 29 to 31
4.d | Review sprint 2 objectives and deliverables
4.x | Project Management | bar: 29 to 31
August
Task Number | Task Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
MIlestone 4 | Development Sprint 2 | bar: 9
4.a | Identify targets for Sprint 2
4.b | Perform sprint 2 analysis, coding & testing (Clarkson) | bar: 1 to 2; 5 to 9
4.c | Perform sprint 2 analysis, coding & testing | bar: 1 to 2; 5 to 9
4.d | Review sprint 2 objectives and deliverables | bar: 9
4.x | Project Management | bar: 1 to 2; 5 to 9
MIlestone 5 | Development Sprint 3 | bar: 23
5.a | Identify targets for Sprint 3 | bar: 12
5.b | Perform sprint 3 analysis, coding & testing (Clarkson) | bar: 12 to 16; 19 to 23
5.c | Perform sprint 3 analysis, coding & testing | bar: 12 to 16; 19 to 23
5.d | Review sprint 3 objectives and deliverables | bar: 23
5.x | Project Management | bar: 12 to 16; 19 to 23
MIlestone 6 | Development Sprint 4
6.a | Identify targets for Sprint 4 | bar: 26
6.b | Perform sprint 4 analysis, coding & testing (Clarkson) | bar: 26 to 30
6.c | Perform sprint 4 analysis, coding & testing | bar: 26 to 30
6.d | Review sprint 4 objectives and deliverables
6.x | Project Management | bar: 26 to 30
September
Task Number | Task Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
MIlestone 6 | Development Sprint 4 | bar: 9
6.a | Identify targets for Sprint 4
6.b | Perform sprint 4 analysis, coding & testing (Clarkson) | bar: 3 to 6; 9
6.c | Perform sprint 4 analysis, coding & testing | bar: 3 to 6; 9
6.d | Review sprint 4 objectives and deliverables | bar: 9
6.x | Project Management | bar: 3 to 6; 9
Milestone 7 | Demonstrate RMM tool using “bench” MFA client
7.a | Develop test set to be run on MFA bench | bar: 10 to 13; 16
7.b | Run the specified tests | bar: 17 to 19
7.c | Collect test results and calculate RMM effectiveness | bar: 20; 23 to 26
7.d | Prepare final report | bar: 27; 30
7.e | Review final report (Clarkson)
7.x | Project Management | bar: 10 to 13; 16 to 20; 23 to 27; 30
October
Task Number | Task Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Milestone 8 | Demonstrate RMM tool using “bench” MFA client | bar: 11
8.a | Develop test set to be run on MFA bench
8.b | Run the specified tests
8.c | Collect test results and calculate RMM effectiveness
8.d | Prepare final report | bar: 1 to 4; 7 to 11
8.e | Review final report (Clarkson) | bar: 7 to 11
8.x | Project Management | bar: 1 to 4; 7 to 11

## Cost - Total
Item | Cost
Labor and Miscellaneous | 125830
Materials, Hardware, and Software | 2400
Travel | 0
TOTAL COST | 128230
* As per request, originally anticipated travel costs have been removed. The original travel estimates are shown below:
Travel | 4855

## Cost - Labor
Activity | Activity Name | Days | Hours | Cost ($) | Role/Deliverable | Hourly Rate | PSS |  |  |  |  | Contract | Univ
1 | Deliver White Paper on three methodologies | [5 empty] | Sr Rsrch | Architect | Prgrmer | Tester | Prj Mgr | Prgrmer | Lead | Assistant
1.a | Research Bayesian and MaxEnt methodologies | 15 | 20 | 2200 | PSS Senior Researcher | 110 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.b | Research MrE methodology | 15 | 75 | 12375 | University Lead Researcher | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 12375 | 0
1.b | Research MrE methodology | 15 | 120 | 4800 | University Graduate Student Researcher | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800
1.c | Complete White Paper | 5 | 20 | 2200 | PSS Senior Researcher | 110 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.d | Clarkson review of White Paper | 2 | 16 | 2640 | University Lead Researcher | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 2640 | 0
1.x | Project Management | 20 | 20 | 1800 | PSS Project Manager | 90 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0
1 | Milestone 1 Totals | 20 | 271 | 26015 | Deliverable: Statistical Methods Whitepaper |  | 4400 | 0 | 0 | 0 | 1800 | 0 | 15015 | 4800 | 6200 | 0 | 19815 | 26015
Program Review required before proceeding to next milestone
2 | Develop specifications for MrE algorithm
2.a | Identify basic interface requirements of components | 12 | 12 | 1320 | PSS Senior Researcher | 110 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.a | Identify basic interface requirements of components | 12 | 0 | 0 | PSS Application Architect | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.b | Identify basic interface requirements of components (Sub) | 12 | 56 | 4200 | Contract Programmer | 75 | 0 | 0 | 0 | 0 | 0 | 4200 | 0 | 0
2.c | Identify basic interface requirements of components (Univ) | 12 | 44 | 7260 | University Lead Researcher | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 7260 | 0
2.d | Specify high-level requirements for "problem model" | 12 | 12 | 1320 | PSS Senior Researcher | 110 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.d | Specify high-level requirements for "problem model" | 12 | 0 | 0 | PSS Application Architect | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.e | Specify high-level requirements for "problem model" (Sub) | 12 | 56 | 4200 | Contract Programmer | 75 | 0 | 0 | 0 | 0 | 0 | 4200 | 0 | 0
2.f | Specify high-level requirements for "problem model" (Univ) | 12 | 44 | 7260 | University Lead Researcher | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 7260 | 0
2.g | Specify first-pass minimum API requirements | 5 | 17 | 1870 | PSS Application Architect | 110 | 0 | 1870 | 0 | 0 | 0 | 0 | 0 | 0
2.h | Specify first-pass minimum API requirements (Sub) | 5 | 30 | 2250 | Contract Programmer | 75 | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 0
2.x | Project Management | 15 | 15 | 1350 | PSS Project Manager | 90 | 0 | 0 | 0 | 0 | 1350 | 0 | 0 | 0
2 | Milestone 2 | 17 | 286 | 31030 | Deliverable: RMM & Bench Preliminary Specifications |  | 2640 | 1870 | 0 | 0 | 1350 | 10650 | 14520 | 0 | 5860 | 10650 | 14520 | 31030
Program Review required before proceeding to next milestone
3.a | Identify targets for Sprint 1 | 1 | 4 | 300 | PSS Application Programmer | 75 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0
3.b | Identify targets for Sprint 1 (Sub) | 1 | 4 | 300 | Contract Programmer | 75 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0
3.c | Perform sprint 1 analysis, coding & testing | 10 | 10 | 1100 | PSS Application Architect | 110 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0
3.c | Perform sprint 1 analysis, coding & testing | 10 | 20 | 1500 | PSS Application Programmer | 75 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0
3.d | Perform sprint 1 analysis, coding & testing (Sub) | 10 | 60 | 4500 | Contract Programmer | 75 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0
3.e | Perform sprint 1 analysis, coding & testing (Univ) | 10 | 11 | 1815 | University Lead Researcher | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 1815 | 0
3.e | Perform sprint 1 analysis, coding & testing (Univ) | 10 | 10 | 400 | University Graduate Student Researcher | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400
3.f | Review sprint 1 objectives and deliverables | 1 | 4 | 440 | PSS Application Architect | 110 | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0
3.g | Review sprint 1 objectives and deliverables (Sub) | 1 | 4 | 300 | Contract Programmer | 75 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0
3.x | Project Management | 10 | 15 | 1350 | PSS Project Manager | 90 | 0 | 0 | 0 | 0 | 1350 | 0 | 0 | 0
3 | Milestone 3 | 10 | 142 | 12005 | Deliverable: RMM & Bench - Iteration 1 |  | 0 | 1540 | 1800 | 0 | 1350 | 5100 | 1815 | 400 | 4690 | 5100 | 2215 | 12005
Program Review required before proceeding to next milestone
4.a | Identify targets for Sprint 1 | 1 | 4 | 300 | PSS Application Programmer | 75 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0
4.b | Identify targets for Sprint 1 (Sub) | 1 | 4 | 300 | Contract Programmer | 75 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0
4.c | Perform sprint 1 analysis, coding & testing | 10 | 5 | 550 | PSS Application Architect | 110 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0
4.c | Perform sprint 1 analysis, coding & testing | 10 | 20 | 1500 | PSS Application Programmer | 75 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0
4.d | Perform sprint 1 analysis, coding & testing (Sub) | 10 | 60 | 4500 | Contract Programmer | 75 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0
4.e | Perform sprint 1 analysis, coding & testing (Univ) | 10 | 12 | 1980 | University Lead Researcher | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 1980 | 0
4.e | Perform sprint 1 analysis, coding & testing (Univ) | 10 | 10 | 400 | University Graduate Student Researcher | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400
4.f | Review sprint 1 objectives and deliverables | 1 | 4 | 440 | PSS Application Architect | 110 | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0
4.g | Review sprint 1 objectives and deliverables (Sub) | 1 | 4 | 300 | Contract Programmer | 75 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0
4.x | Project Management | 10 | 20 | 1800 | PSS Project Manager | 90 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0
4 | Milestone 4 | 10 | 143 | 12070 | Deliverable: RMM & Bench - Iteration 2 |  | 0 | 990 | 1800 | 0 | 1800 | 5100 | 1980 | 400 | 4590 | 5100 | 2380 | 12070
Program Review required before proceeding to next milestone
5.a | Identify targets for Sprint 1 | 1 | 4 | 300 | PSS Application Programmer | 75 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0
5.b | Identify targets for Sprint 1 (Sub) | 1 | 4 | 300 | Contract Programmer | 75 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0
5.c | Perform sprint 1 analysis, coding & testing | 10 | 0 | 0 | PSS Application Architect | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.c | Perform sprint 1 analysis, coding & testing | 10 | 10 | 750 | PSS Application Programmer | 75 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0
5.d | Perform sprint 1 analysis, coding & testing (Sub) | 10 | 60 | 4500 | Contract Programmer | 75 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0
5.e | Perform sprint 1 analysis, coding & testing (Univ) | 10 | 11 | 1815 | University Lead Researcher | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 1815 | 0
5.e | Perform sprint 1 analysis, coding & testing (Univ) | 10 | 10 | 400 | University Graduate Student Researcher | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400
5.f | Review sprint 1 objectives and deliverables | 1 | 4 | 440 | PSS Application Architect | 110 | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0
5.g | Review sprint 1 objectives and deliverables (Sub) | 1 | 4 | 300 | Contract Programmer | 75 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0
5.x | Project Management | 10 | 20 | 1800 | PSS Project Manager | 90 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0
5 | Milestone 5 | 10 | 127 | 10605 | Deliverable: RMM & Bench - Iteration 3 |  | 0 | 440 | 1050 | 0 | 1800 | 5100 | 1815 | 400 | 3290 | 5100 | 2215 | 10605
Program Review required before proceeding to next milestone
6.a | Identify targets for Sprint 1 | 1 | 4 | 300 | PSS Application Programmer | 75 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0
6.b | Identify targets for Sprint 1 (Sub) | 1 | 4 | 300 | Contract Programmer | 75 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0
6.c | Perform sprint 1 analysis, coding & testing | 10 | 0 | 0 | PSS Application Architect | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.c | Perform sprint 1 analysis, coding & testing | 10 | 10 | 750 | PSS Application Programmer | 75 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0
6.d | Perform sprint 1 analysis, coding & testing (Sub) | 10 | 60 | 4500 | Contract Programmer | 75 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0
6.e | Perform sprint 1 analysis, coding & testing (Univ) | 10 | 11 | 1815 | University Lead Researcher | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 1815 | 0
6.e | Perform sprint 1 analysis, coding & testing (Univ) | 10 | 10 | 400 | University Graduate Student Researcher | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400
6.f | Review sprint 1 objectives and deliverables | 1 | 4 | 440 | PSS Application Architect | 110 | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0
6.g | Review sprint 1 objectives and deliverables (Sub) | 1 | 4 | 300 | Contract Programmer | 75 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0
6.x | Project Management | 10 | 20 | 1800 | PSS Project Manager | 90 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0
6 | Milestone 6 | 10 | 127 | 10605 | Deliverable: RMM & Bench - Iteration 4 |  | 0 | 440 | 1050 | 0 | 1800 | 5100 | 1815 | 400 | 3290 | 5100 | 2215 | 10605
Program Review required before proceeding to next milestone
7 | Demonstrate RMM tool using “bench” MFA client
7.a | Develop test set to be run on MFA bench | 5 | 20 | 2200 | PSS Senior Researcher | 110 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.b | Run the specified tests | 3 | 0 | 0 | PSS Senior Researcher | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.b | Run the specified tests | 3 | 12 | 900 | PSS Application Programmer | 75 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0
7.b | Run the specified tests | 3 | 60 | 2700 | PSS Application Tester | 45 | 0 | 0 | 0 | 2700 | 0 | 0 | 0 | 0
7.c | Collect test results and calculate RMM effectiveness | 5 | 20 | 2200 | PSS Senior Researcher | 110 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.d | Prepare final report | 10 | 40 | 4400 | PSS Senior Researcher | 110 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.e | Review final report (Univ) | 5 | 40 | 6600 | University Lead Researcher | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 0
7.e | Project Management | 23 | 50 | 4500 | PSS Project Manager | 90 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0
7 | Milestone 7 | 23 | 242 | 23500 | Deliverable: Final Project Report & Analysis |  | 8800 | 0 | 900 | 2700 | 4500 | 0 | 6600 | 0 | 16900 | 0 | 6600 | 23500
Final Program Review | [6 empty] | PSS |  |  |  |  | Contract | Univ
[7 empty] | Sr Rsrch | Architect | Prgrmer | Tester | Prj Mgr | Prgrmer | Lead | Assistant
| PROJECT TOTALS |  | 1338 | 125830 |  |  | 15840 | 5280 | 6600 | 2700 | 14400 | 31050 | 43560 | 6400 | 44820 | 31050 | 49960 | 125830

## Roles and Rates
Role Name | Role Description | Hourly Billing Rate | Justification
PSS Administrative Manager | Responsible for officially representing ProvenSecure Solutions (e.g. by formally signing off on committments | 150 | Prevailing East Coast market rate for the position (independent contractor rates used as guide since ProvenSecure not currently providing any non-salary benefits).
PSS Senior Researcher | Responsible for defining the main research objectives of the projec and coordinating efforts o fother contract or university researchers involved in a project.. Acts as the "customer" -- defining and/or approving requirements and functional specification. Heavily involved in JAD style implementations, working with architects and programmers. | 110 | Prevailing East Coast market rate for the position (independent contractor rates used as guide since ProvenSecure not currently providing any non-salary benefits). ($150)
PSS Program Manager | Maintains control over full portfolio of projects being performed by ProvenSecure. Responsible for portfolio budgeting, selection and sequencing of appropriate projects, and working to provide adequate staff for various efforts. | 150 | Prevailing East Coast market rate for the position (independent contractor rates used as guide since ProvenSecure not currently providing any non-salary benefits).
PSS Project Manager | Maintains control over single, relatively small project being performed by ProvenSecure. | 90 | Prevailing East Coast market rate for the position (independent contractor rates used as guide since ProvenSecure not currently providing any non-salary benefits).
PSS Senior Network Engineer | Takes a lead role in the analysis and implementation of network security components. For network security research projects, this is the role responsible for a thorough understanding of network communications and protocols, and methods of analyzing and securing those communications. | 150 | Prevailing East Coast market rate for the position (independent contractor rates used as guide since ProvenSecure not currently providing any non-salary benefits).
PSS Senior Application Architect | Takes a lead role in the analysis and implementation of applications/solutions. Responsible for converting the vision and requirements of the Lead Researcher into technical specifications that an Application Programmer can realize. More than an analyst -- assumes a working knowledge of the technical nuances of security system environments. | 150 | Prevailing East Coast market rate for the position (independent contractor rates used as guide since ProvenSecure not currently providing any non-salary benefits).
PSS Application Architect | Responsible for converting the vision and requirements of the Lead Researcher into technical specifications that an Application Programmer can realize. More than an analyst -- assumes a working knowledge of the technical nuances of security system environments. | 110 | Prevailing East Coast market rate for the position (independent contractor rates used as guide since ProvenSecure not currently providing any non-salary benefits). ($125)
PSS Small Project Manager | Maintains control over project budget and schedule. Ensures project proceeds according to plan . Responsible for working with Lead Researcher and external customer (if any) to ensure that the project plan will deliver the correct product(s) within the specified budget and time frame. | 90 | Prevailing East Coast market rate for the position (independent contractor rates used as guide since ProvenSecure not currently providing any non-salary benefits).
PSS System (Hardware) Manager | Responsible for installing, configuring and maintaining any hardware and peripherals owned by ProvenSecure. Responsible for installing and maintaining support software (i.e. Trac) necessary for ProvenSecure to conduct daily business. | 80 | Prevailing East Coast market rate for the position (independent contractor rates used as guide since ProvenSecure not currently providing any non-salary benefits).
PSS Documentation / Change Control Manager | Ensures project documentation is properly generated and stored. Ensures documents are placed under appropriate change controls and monitors compliance with change control procedures. | 75 | Prevailing East Coast market rate for the position (independent contractor rates used as guide since ProvenSecure not currently providing any non-salary benefits).
PSS Network Engineer | Responsible for configuring and maintaining the network environment needed by ProvenSecure This includes maintaining ISP relationships, managing domain services, cloud services, etc. | 75 | Prevailing East Coast market rate for the position (independent contractor rates used as guide since ProvenSecure not currently providing any non-salary benefits).
PSS Application Programmer | Responsible for creating the actual working bench systems, prototypes, and/or finished "production" systems identified as project deliverables. | 75 | Prevailing East Coast market rate for the position (independent contractor rates used as guide since ProvenSecure not currently providing any non-salary benefits).
PSS Web Designer | Responsible for designing, deploying, and maintaining the ProvenSecure website. | 70 | Prevailing East Coast market rate for the position (independent contractor rates used as guide since ProvenSecure not currently providing any non-salary benefits).
PSS Junior Application Programmer | Resonsible for completing coding tasks under the supervision of an Application Programmer, System Manager, Network Administrator or Web Designer | 45 | Prevailing East Coast market rate for the position (independent contractor rates used as guide since ProvenSecure not currently providing any non-salary benefits).
PSS Application Tester | Responsible for conducting acceptance tests of delivered systems . For statistical analysis projects, responsible for conducting tests of systems being analyzed. | 45 | Prevailing East Coast market rate for the position (independent contractor rates used as guide since ProvenSecure not currently providing any non-salary benefits).
Role Name | Role Description | Hourly Rate | Justification
Contract Programmer | Responsible for creating the actual working bench systems, prototypes, and/or finished "production" systems identified as project deliverables. | 75 | Agreed upon rate
Role Name | Role Description | Hourly Rate | Justification
University Lead Researcher | Responsible for providing in-depth technical expertise -- primarily in a research capacity -- for a given project Responsible for developing mathematical algorithms and/or data processing paradigms that are of use to the security systems community. | 165 | Prevailing rate for professorial-level university researchers (needs to include "university overhead")
University Post-Doctorate Researcher | Responsible for performing basic research and documentation under the guidance of the University Lead Researcher | 105 | Prevailing rate for student researchers (needs to include "university overhead")
University Graduate Student Researcher | Responsible for performing basic research and documentation under the guidance of the University Lead Researcher | 40 | Prevailing rate for student researchers (needs to include "university overhead")

## Cost - Materials
Item | Quantity | Unit Cost | Total Cost
Cloud Services | 4 months | 100 | 400
Authentication Service licenses | 4 | 500 | 2000
|  | TOTAL | 2400

## Cost - Travel
From | To | Airfare | Lodging | Per Diem | Rental Car | Misc. | Days | Cost/Trip | Trips | Total Travel
Newark, NJ | Arlington, VA | 0 | 224 | 39 |  | 300 | 2 | 826 | 2 | 1652
Greenville, SC | Arlington, VA | 200 | 224 | 39 | 75 | 25 | 2 | 901 | 2 | 1802
Potsdam, NY | Arlington, VA | 600 | 224 | 39 | 75 | 125 | 2 | 1401 | 1 | 1401
[9 empty] | Total | 4855
*Misc includes tolls, airport parking, etc.
Assumes...
2 trips for team member from Greenville, SC to Washington DC area
2 trips for team member from New Jersey to Washington DC area
1 trips for Adom Giffin from Clarkson University to Washington DC area
MIleage rate for personal vehicle usage = $0.565 per mile