## Schedule
June
Activity | Activity Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Milestone 1 | Prepare White Paper on three methodologies | bar: 1 to 23
1.a | Research Bayesian and MaxEnt methodologies
1.b | Research MrE methodology (Clarkson)
1.c | Complete White Paper | bar: 1 to 23
1.d | Clarkson review of White Paper (Clarkson) | bar: 1 to 23
1.x | Project Management
Milestone 2 | Identify initial requirements for RMM and "bench tester" | bar: 1 to 23
2.a | Identify basic interface requirements of components
2.b | Identify basic interface requirements of components (Sub)
2.c | Identify basic interface requirements of components (Univ)
2.d | Specify high-level requirements for "problem model"
2.e | Specify high-level requirements for "problem model" (Sub)
2.f | Specify high-level requirements for "problem model" (Univ)
2.g | Specify first-pass minimum API requirements | bar: 1 to 23
2.h | Specify first-pass minimum API requirements (Sub) | bar: 1 to 23
2.x | Project Management
July
Activity | Activity Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Milestone 1 | Prepare White Paper on three methodologies | bar: 18
1.a | Research Bayesian and MaxEnt methodologies | bar: 1 to 3; 5; 8 to 12; 15
1.b | Research MrE methodology (Clarkson) | bar: 1 to 3; 5; 8 to 12; 15
1.c | Complete White Paper | bar: 12; 15 to 18
1.d | Clarkson review of White Paper (Clarkson) | bar: 17 to 18
1.x | Project Management | bar: 1 to 3; 5; 8 to 12; 15 to 18
Milestone 2 | Identify initial requirements for RMM and "bench tester" | bar: 12
2.a | Identify basic interface requirements of components | bar: 1 to 3; 5; 8 to 10
2.b | Identify basic interface requirements of components (Sub) | bar: 1 to 3; 5; 8 to 10
2.c | Identify basic interface requirements of components (Univ) | bar: 1 to 3; 5; 8 to 10
2.d | Specify high-level requirements for "problem model" | bar: 1 to 3; 5; 8 to 10
2.e | Specify high-level requirements for "problem model" (Sub) | bar: 1 to 3; 5; 8 to 10
2.f | Specify high-level requirements for "problem model" (Univ) | bar: 1 to 3; 5; 8 to 10
2.g | Specify first-pass minimum API requirements | bar: 8 to 12
2.h | Specify first-pass minimum API requirements (Sub) | bar: 8 to 12
2.x | Project Management | bar: 1 to 3; 5; 8 to 12
MIlestone 3 | Development Sprint 1 | bar: 26
3.a | Identify targets for Sprint 1 | bar: 15
3.b | Identify targets for Sprint 1 (Sub) | bar: 15
3.c | Perform sprint 1 analysis, coding & testing | bar: 15 to 19; 22 to 26
3.d | Perform sprint 1 analysis, coding & testing (Sub) | bar: 15 to 19; 22 to 26
3.e | Perform sprint 1 analysis, coding & testing (Univ) | bar: 15 to 19; 22 to 26
3.f | Review sprint 1 objectives and deliverables | bar: 26
3.g | Review sprint 1 objectives and deliverables (Sub) | bar: 26
3.x | Project Management | bar: 15 to 19; 22 to 26
MIlestone 4 | Development Sprint 2
4.a | Identify targets for Sprint 2 | bar: 29
4.b | Perform sprint 2 analysis, coding & testing (Clarkson) | bar: 29 to 31
4.c | Perform sprint 2 analysis, coding & testing | bar: 29 to 31
4.d | Review sprint 2 objectives and deliverables
4.x | Project Management | bar: 29 to 31
August
Task Number | Task Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
MIlestone 4 | Development Sprint 2 | bar: 9
4.a | Identify targets for Sprint 2
4.b | Perform sprint 2 analysis, coding & testing (Clarkson) | bar: 1 to 2; 5 to 9
4.c | Perform sprint 2 analysis, coding & testing | bar: 1 to 2; 5 to 9
4.d | Review sprint 2 objectives and deliverables | bar: 9
4.x | Project Management | bar: 1 to 2; 5 to 9
MIlestone 5 | Development Sprint 3 | bar: 23
5.a | Identify targets for Sprint 3 | bar: 12
5.b | Perform sprint 3 analysis, coding & testing (Clarkson) | bar: 12 to 16; 19 to 23
5.c | Perform sprint 3 analysis, coding & testing | bar: 12 to 16; 19 to 23
5.d | Review sprint 3 objectives and deliverables | bar: 23
5.x | Project Management | bar: 12 to 16; 19 to 23
MIlestone 6 | Development Sprint 4
6.a | Identify targets for Sprint 4 | bar: 26
6.b | Perform sprint 4 analysis, coding & testing (Clarkson) | bar: 26 to 30
6.c | Perform sprint 4 analysis, coding & testing | bar: 26 to 30
6.d | Review sprint 4 objectives and deliverables
6.x | Project Management | bar: 26 to 30
September
Task Number | Task Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
MIlestone 6 | Development Sprint 4 | bar: 9
6.a | Identify targets for Sprint 4
6.b | Perform sprint 4 analysis, coding & testing (Clarkson) | bar: 3 to 6; 9
6.c | Perform sprint 4 analysis, coding & testing | bar: 3 to 6; 9
6.d | Review sprint 4 objectives and deliverables | bar: 9
6.x | Project Management | bar: 3 to 6; 9
Milestone 7 | Demonstrate RMM tool using “bench” MFA client
7.a | Develop test set to be run on MFA bench | bar: 10 to 13; 16
7.b | Run the specified tests | bar: 17 to 19
7.c | Collect test results and calculate RMM effectiveness | bar: 20; 23 to 26
7.d | Prepare final report | bar: 27; 30
7.e | Review final report (Clarkson)
7.x | Project Management | bar: 10 to 13; 16 to 20; 23 to 27; 30
October
Task Number | Task Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Milestone 8 | Demonstrate RMM tool using “bench” MFA client | bar: 11
8.a | Develop test set to be run on MFA bench
8.b | Run the specified tests
8.c | Collect test results and calculate RMM effectiveness
8.d | Prepare final report | bar: 1 to 4; 7 to 11
8.e | Review final report (Clarkson) | bar: 7 to 11
8.x | Project Management | bar: 1 to 4; 7 to 11