## Risks
Risk ID | Probability of Occurrence | Disruption Potential | Risk Score | Last Reviewed | Risk Short Name | Risk Description | Mitigation Strategy
R3 | Resolved / Avoided | Medium | 0 | 2013-10-06 | Clarkson availability | Dr. Giffon’s availability may wane toward the end of the project due to teaching demands on his time as fall semester gets underway. | Dr. Giffon has worked out a schedule to ensure we have access as needed to finish data analysis and reporting.
R2 | Resolved / Avoided | Significant | 0 | 2013-07-21 | Insufficient authenticator APIs | Commercially available products may not offer the information we need via their APIs. | AT&T Voice, AT&T Face, and BetaFace have all been identified as returning a ranged "score" that can be used for examination in the project.
R5 | Resolved / Avoided | Significant | 0 | 2013-07-21 | Export Control | Particulars regarding exchange of information with foreign-sited contractor may be constrained by federal Export Control regulations | Research complete; no export control issues appear to exist.
R7 | Resolved / Avoided | Medium | 0 | 2013-07-21 | Repository | A repository capable of providing necessary version controls is not yet in place - and will be needed before the completion of Sprint 1 | For this effort, we will use the GitHub "Bronze" level solution, which will cost us $25 per month and will allow us to configure access as needed. Individuals needing acccess will install free Git clients. Long term (beyond this project) we will likely migrate to SubVersion.
R4 | Resolved / Avoided | Showstopper | 0 | 2013-07-28 | No demonstration platform | Difficulty in procuring an adequate .NET-based deployment/test environment in time for the first sprint results to be properly demonstrated and tested. | Work underway to secure a cloud-based Windows Virtual Machine platform that all can access as needed. This machine will be populated with necesasry software components, and the build process will be documented.
R1 | Resolved / Avoided | Minimal | 0 | 2013-08-04 | Too much from product | Customer will desire to implement resulting product “as is”. | Ensure that all documentation makes it clear that all components of product are proof-of-concept, not production-ready.
R6 | Resolved / Avoided | Medium | 0 | 2013-08-25 | Code Transfer / Communication | Potential for confusion to arise revolving around transfer of documents, code, and executable images from person to person since we lack a central development environment. | Once GitHub is in place, "rules" for its use will be published.
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## Issues
Issue ID | Disruption Potential | Issue Score | Last Reviewed | Issue Status | Issue Short Name | Issue Description | Mitigation Strategy
I6 | Significant | 25 | 2013-10-06 | Open / Active | Virtual Camera and Microphone Unstable | The software purchased to make cameras and microphones available on virtual machine are not working as hoped | Work with the new software to see if issues can be resolved.
I4 | Significant | 25 | 2013-09-22 | Closed / Resolved | AT&T Face Authentication API unstable | The AT&T authenticators are not "commercially available"; they are available through the AT&T Foundry. There have been some issues with the API. | AT&T Face API is proving to be a "moving target". (The product is not yet commercial-ready.) Decision made to abandon and go with just Betaface.
I5 | Significant | 25 | 2013-09-22 | Closed / Resolved | BetaFace Authentication not working as anticipated | Documentation for the API is sparse; getting it to work as expected has proven difficult. | Sprint 5 deployed working interface.
I3 | Significant | 25 | 2013-09-15 | Closed / Resolved | Voice Authentication API unstable | The AT&T authenticators are not "commercially available"; they are available through the AT&T Foundry. There have been some issues with the Voice API (determining proper usage) and with the availability of the AT&T environment itself | API issues resolved and interface working in Bench
I2 | Significant | 25 | 2013-08-25 | Closed / Resolved | Logitech Cameras do not "cross over" to remote server system | The Bench running on our AWS test system cannot "see" Logitech cameras on remote workstations -- and most PSS people are using Logitech cameras. (Only "true plug and play" devices bridge.) | FabulaTech products (one for camera, one for microphone) resolve the issue.
I1 | Minimal | 1 | 2013-07-28 | Closed / Resolved | Development team geography | Development Team distribution across multiple time zones makes communication planning difficult | Commuication Plan is being developed that will allow for "disconnected" standup meetings as required where significant timezone differences exist. (Project Manager will facilitate and ensure all team members are up to date about all issues.
I3
I4
I5
I6
I7
I8
I9
I10
I11
I12
I13

## Lookups (hidden)
Probability of Occurrence
Resolved / Avoided | 0
Low | 1
Medium | 3
High | 5
Certain | 9
Unassigned | 9
Disruption Potential
None | 0
Minimal | 1
Medium | 3
Significant | 5
Showstopper | 9
Unassigned | 9
Issue Status
Open / Active
Closed / Resolved