## Risks
Risk ID | Probability of Occurrence | Disruption Potential | Risk Score | Last Reviewed | Risk Short Name | Risk Description | Mitigation Strategy
R4 | Medium | Showstopper | 27 | 2013-07-14 | No demonstration platform | Difficulty in procuring an adequate .NET-based deployment/test environment in time for the first sprint results to be properly demonstrated and tested. | Work underway to secure a cloud-based Windows Virtual Machine platform that all can access as needed. This machine will be populated with necesasry software components, and the build process will be documented.
R2 | High | Significant | 25 | 2013-07-14 | Insufficient authenticator APIs | Commercially available products may not offer the information we need via their APIs. | Broad sweep market research to see what’s out there. Use of some simple factors that we can control – and which we can ensure provide the desired interface Simulation of authentication results based on published studies of either specific product or authentication method reliability.
R3 | Medium | Medium | 9 | 2013-07-14 | Clarkson availability | Dr. Giffon’s availability may wane toward the end of the project due to teaching demands on his time as fall semester gets underway. | Keep the project on schedule. Reschedule if necessary
R5 | Low | Significant | 5 | 2013-07-14 | Export Control | Particulars regarding exchange of information with foreign-sited contractor may be constrained by federal Export Control regulations | Obtain definitive opinions regarding applicability of Export Control requirements; formulate ultimate plan of action if the need arises.
R1 | Medium | Minimal | 3 | 2013-07-14 | Too much from product | Customer will desire to implement resulting product “as is”. | Ensure that all documentation makes it clear that all components of product are proof-of-concept, not production-ready.
R6 | Low | Medium | 3 | 2013-07-14 | Code Transfer / Communication | Potential for confusion to arise revolving around tranfer of documents, code, and executable images from person to person since we lack a central development environment. | Refine the communication plan - and stick to it; secure version control-capable repository for key documentation and source code.
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## Issues
Issue ID | Disruption Potential | Issue Score | Last Reviewed | Issue Status | Issue Short Name | Issue Description | Mitigation Strategy
I1 | Minimal | 1 | 2013-07-21 | Open / Active | Development team geography | Development Team distribution across multiple time zones makes communication planning difficult | Commuication Plan is being developed that will allow for "disconnected" standup meetings as required where significant timezone differences exist. (Project Manager will facilitate and ensure all team members are up to date about all issues.
I2
I3
I4
I5
I6
I7
I8
I9
I10
I11
I12
I13

## Lookups (hidden)
Probability of Occurrence
Resolved / Avoided | 0
Low | 1
Medium | 3
High | 5
Certain | 9
Unassigned | 9
Disruption Potential
None | 0
Minimal | 1
Medium | 3
Significant | 5
Showstopper | 9
Unassigned | 9
Issue Status
Open / Active
Closed / Resolved